Project Planning Phase
Project Planning Template (Product Backlog, Sprint Planning, Stories, Story
points)
Date
21 October 2022
Team ID
PNT2022TMID42400
Project Name
Project - University Admit Eligibility Predictor
Maximum Marks
8 Marks
Product Backlog, Sprint Schedule, and Estimation (4 Marks)
Use the below template to create product backlog and sprint schedule
Sprint
Functional
User
User Story / Task
Story
Priority
Team
Requirement
Points
Members
(Epic)
Number
Sprint-1
Registration
USN-1
As a user, I can
2
High
Praveen
kumar
register for the
application by
entering my email,
password, and
confirming my
password.
USN-2
As a user, I will
1
High
prakash
receive confirmation
email once I have
registered for the
application
Sprint-2
USN-3
As a user, I can
2
Low
Usha
rajeshwari
register for the
application through
Facebook
USN-4
As a user, I can
2
Medium
sundari
register for the
application through
Gmail
Login
USN-5
As a user, I can log
1
High
Praveen
kumar
into the application
by entering email &
password
Dashboard
Project Tracker, Velocity & Burndown Chart: (4 Marks)

---
Total
Duration
Sprint End
Story Points
Start Date
Completed
Release Date
(Planned)
(as on
(Actual)
Planned End
Date)
20
6 Days
24 Oct
29 Oct 2022
20
29 Oct 2022
2022
20
6 Days
31 Oct
05 Nov 2022
2022
Sprint-3
20
6 Days
07 Nov
12 Nov 2022
2022
Sprint-4
20
6 Days
14 Nov
19 Nov 2022
2022
Velocity:
Imagine we have a 10-day sprint duration, and the velocity of the team is 20 (points per sprint).
Let’s calculate the team’s average velocity (AV) per iteration unit (story points per day)
Burndown Chart:
A burn down chart is a graphical representation of work left to do versus time. It is often used in
agile software development methodologies such as Scrum. However, burn down charts can be
applied to any project containing measurable progress over time.
https://www.visual-paradigm.com/scrum/scrum-burndown-chart/
https://www.atlassian.com/agile/tutorials/burndown-charts

---
Reference:
https://www.atlassian.com/agile/project-management
https://www.atlassian.com/agile/tutorials/how-to-do-scrum-with-jira-software
https://www.atlassian.com/agile/tutorials/epics
https://www.atlassian.com/agile/tutorials/sprints
https://www.atlassian.com/agile/project-management/estimation