Project Design Phase-II
Data Flow Diagram & User Stories
Date
05 October 2022
Team ID
PNT2022TMID42400
Project Name
University Admit Eligibility Predictor
Maximum Marks
4 Marks
Data Flow Diagrams:
A Data Flow Diagram (DFD) is a traditional visual representation of the information flows within a system. A neat and clear DFD can depict the right
amount of the system requirement graphically. It shows how data enters and leaves the system, what changes the information, and where data is
stored.

---
User Stories
User Type
Functional
User Story
User Story / Task
Acceptance criteria
Priority
Release
Requirement
Number
(Epic)
Customer
Dashboard
USN-1
As a user, I can view the cut off marks of
I can access and
High
Sprint-1
(Student)
previous years in my dashboard
download the files
USN-2
As a user, I can view university details and
I can only view(read-only)
Medium
Sprint-1
their rankings
USN-3
As a user, I can review the experience of the
I can access the review
Medium
Sprint-2
students in the university
sections
USN-4
As a user, I can upload my documents
I have read and write
High
Sprint-1
access to upload files
USN-5
As a user,I can fill out the general and
I have read and write
High
Sprint-2
educational details in the form provided
access to the forms filled
Predictor
USN-6
I can view the list of universities in which I am
I can receive the final
High
Sprint-2
eligible to get an admission
result as whether eligible
or not
USN-7
I can view the list of universities I am eligible
I can access the files with
Medium
Sprint-2
with the same cut-off but in previous years
read-only permission
Administrator
Dashboard
USN-8
As an administrator,I can have access to
I can have access to read
High
Sprint-3
update the latest updates of the universities
and write the university
information in the
dashboard
USN-9
As an administrator,I can access any
I can access the resources
Medium
Sprint-3
resources available in the page
that are available
USN-10
As an administrator,I can have a track on the
I can access the list of the
High
Sprint-3
universities the student is eligible to get
universities obtained as
admission at
final result